## Sheet1
Week wise plan for January
Week 1	Week 2	Week 3	Week 4

Search for datasets	Visualize data	Training-Testing data split	PCA module

Select relevant dataset	Find correlation	Normalization module	Testing of PCA module

Start preprocessing	Finish preprocessing	Test normalization module	Calculate PCA for the data

Week wise plan for February
Week 1	Week 2	Week 3	Week 4

Regression module	Training the regressoin model	Changing model parameters	Integrating all modules together

Testing the regression module	Evaluating the regression model	Evaluating the regression model	Testing entire system